## UAT Items List
Result coding: 1 = Pass (full functionality with no unexpected errors), 0 = Fail (lack of required functionality or reproducible error during testing), 9 = Conditional (partial functionality, error during testing which cannot be reproduced, poor user experience or other constraints) X = Functionality which is desirable for future iterations of the system. these items are not necessary for user acceptance of this version of the system
# | Test description | Test Protocol | Pass (all items) | Fail (on any item) | User | Test time | Result | Notes | User | Test time | Result | Notes
SUBJECTS
2.1 | New Subjects
2.1.1 | A user with "Subject Data Manager" access to a study can define new subjects. | 1. Log in as a user with "Subject Data Manager" access to WARTN. 2. Click on the WARTN study in the Study Details tab. 3. Click on the "New" button in the Subject > Demographic Data tab. 4. Enter relevant data for required fields marked with an asterisk and click the "Save" button. | 1. The user is able to create a new subject. 2. The new subject is unable to be identified as a subject in the WARTN study. | 1. The user is unable to create a new subject. 2. The new subject is unable to be identified as a subject in the WARTN study. |  |  |  |  | cellis | 2013-03-05 12:50 | 1 | new subject created successfully
2.1.2 | A user with "Subject Read-Only" access to a study cannot define new subjects. | 1. Log in as a user with "Subject Read-Only" access to WARTN. 2. Click on the WARTN study in the Study Details tab. 3. Click on the "New" button in the Subject > Demographic Data tab. 4. Enter relevant data for required fields marked with an asterisk and click the "Save" button. | 1. The user is unable to create a new subject. | 1. The user is unable to create a new subject. |  |  |  |  | cellis | 2013-03-05 12:50 | 1 | unable to create new subjects
Numbering
| The database allows for sequential patient numbering across all studies and substudies (P01234). | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab (note that this is an auto-incrementing SubjectUID study). 3. Click theSubject Tab 4. Click new and create subject, then his save. Note the Subject UID. 5. Repeat step 4, and see if the resultant subject UID has incremented by one | 1. Subsequently created SubjectUIDs should be incremented by one, and follow the pattern laid out in the study details page | 1. Subsequently created SubjectUIDs should be incremented by one, and follow the pattern laid out in the study details page | lisa | 2013-03-05 12:50 | 1 | same as wager. If we can have them "P01234" instead of "WTN-012345678" that'd be best for us really. | cellis | 2013-03-05 12:50 | 1 | subject identification can be set to requested format
Fields
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "title" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:50 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "first name" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:50 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "surname" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:50 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "middle name" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:50 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "preferred name" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:50 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "previous surname" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:50 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "date of birth" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:50 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "date of death" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:50 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "contact phone #" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:50 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "other ID" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:50 | 9 |  |  |  | 1 | Can use custom fields to store otherid
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "gender" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:50 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "address" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Click “Address” tab. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:50 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "suburb" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Click “Address” tab. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:57 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "postcode" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Click “Address” tab. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:57 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "state" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Click “Address” tab. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:57 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "country" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Click “Address” tab. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:57 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "date last known alive" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:57 | 1 | Can add as subject-specific custom field |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "mortality status" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:57 | 9 | Can use “field “Vital Status” |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "date of death" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:59 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "cause of death" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:59 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "comments" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:59 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "marital status" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:59 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "subject status" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:59 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "consent status" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:59 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for entry of subject "consent type" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:59 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for listing the subject "consent history" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:59 | 1 |  |  |  | 1
| The "Subject > Demographic Data" page for a specific subject contains an appropriate field for listing the subject "study consent list" | 1. Log in as a user with access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | lisa | 2013-03-05 12:59 | 9 | List of assigned sub-studies displayed for particular subject. |  |  | 1
Search
| A user with "Subject Read-Only" or higher access to a study can search for a subject using any field or ID associated with that subject, and view the Subject > Demographic Data form for a found subject. | 1. Log in as a user with "Subject Read-Only" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Identify if the Subject > Demographic Data tab allows for the user to search for subjects based on data from all subject fields. | 1. The user is able to search for data on every subject field. 2. The user is able to find and identify subjects by searching for data from any subject field. 3. The user is able to click into the Subject > Demographic Data form for a subject found by searching any subject field. | 1. The user is unable to search for data on one or more subject fields. 2. The user is unable to find and identify subjects by searching for data from a subject field. 3. The user is unable to click into the Subject > Demographic Data form for a subject found by searching any subject field. |  |  |  | searching is important |  |  | x | Part of Data Extraction. To be implemented in future milestone
| A user with "Subject Read-Only" or higher access to a study can search for a subject by collection ID or biospecimen ID, and view the Subject > Demographic Data form for a found subject. | 1. Log in as a user with "Subject Read-Only" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Identify if the Subject > Demographic Data tab allows for the user to search for subjects via collection ID and biospecimen ID. | 1. The user is able to search for data on every subject field. 2. The user is able to find and identify subjects by searching for a collection ID 3. The user is able to find and identify subjects by searching for a biospecimen ID. 4. The user is able to click into the Subject > Demographic Data form for a subject found by searching collection ID and biospecimen ID. | 1. The user is unable to search for data on one or more subject fields. 2. The user is unable to find and identify subjects by searching for a collection ID. 3. The user is unable to find and identify subjects by searching for a biospecimen ID. 4. The user is unable to click into the Subject > Demographic Data form for a subject found by searching collection ID and biospecimen ID. |  |  |  | searching is important |  |  | 1 | To do this, use the biocollection search, select the bio* and then your subject will be in context.
Attachments
| A user with "Subject Data Manager" or higher access to a study can upload attachments for a subject. | 1. Log in as a user with "Subject Data Manager" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. In Subject > Attachments click "New". 5. Click "browse", find a test image file, and click "Save" to upload it. 6. Identify if the attachment exists for the subject on the Subject > Attachments tab. | 1. The user is able to upload attachments for a subject. 2. The user is able to see a list of previously uploaded attachments for a subject. 3. The user is able to download attachments for a subject. | 1. The user is unable to upload attachments for a subject. 2. The user is unable to see a list of previously uploaded attachments for a subject. 3. The user is unable to download attachments for a subject. | Lisa | 2013-03-05 15:48 | 1 |  |  |  | 1
| A user with "Subject Data Manager" or higher access to a study can delete attachments previously uploaded for a subject. | 1. Log in as a user with "Subject Data Manager" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. In Subject > Attachments click "Delete" on an attachment previously uploaded. 5. Identify the attachment no longer exists for the subject on the Subject > Attachments tab. | 1. The user is able to see a list of previously uploaded attachments for a subject. 2. The user is able to delete attachments previously uploaded for a subject. | 1. The user is unable to see a list of previously uploaded attachments for a subject. 2. The user is unable to delete attachments previously uploaded for a subject. | Lisa | 2013-03-05 15:48 | 1 |  |  |  | 1
| A user with "Subject Read-Only" or higher access to a study can view attachments for a subject. | 1. Log in as a user with "Subject Read Only" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Identify that previously uploaded attachments exist in the Subject > Attachments tab | 1. The user is able to see a list of previously uploaded attachments for a subject. 2. The user is able to download attachments previously uploaded for a subject. | 1. The user is unable to see a list of previously uploaded attachments for a subject. 2. The user is unable to download attachments previously uploaded for a subject. | Lisa | 2013-03-05 15:48 | 1 |  |  |  | 1
| A user with "Subject Read-Only" access to a study cannot upload attachments for a subject. | 1. Log in as a user with "Subject Read-Only" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. In Subject > Attachments click "New". 5. Click "browse", find a test image file, and click "Save" to upload it. 6. Identify if the attachment exists for the subject on the Subject > Attachments tab. | 1. The user is able to see a list of previously uploaded attachments for a subject. 2. The user is unable to upload attachments for a subject. | 1. The user is unable to see a list of previously uploaded attachments for a subject. 2. The user is able to upload attachments for a subject. | Lisa | 2013-03-05 15:48 | 1 |  |  |  | 1
| A user with "Subject Read-Only" access to a study cannot delete attachments previously uploaded for a subject. | 1. Log in as a user with "Subject Read-Only" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. In Subject > Attachments click "Delete" on an attachment previously uploaded. 5. Identify the attachment no longer exists for the subject on the Subject > Attachments tab. | 1. The user is able to see a list of previously uploaded attachments for a subject. 2. The user is unable to delete attachments previously uploaded for a subject. | 1. The user is unable to see a list of previously uploaded attachments for a subject. 2. The user is able to delete attachments previously uploaded for a subject. | Lisa | 2013-03-05 15:48 | 1 |  |  |  | 1
User Experience
| USER EXPERIENCE: When a subject is in context, data from the field "surname" should always be visible. | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | Lisa | 2013-03-05 14:52 | 1 |  |  |  | 1
| USER EXPERIENCE: When a subject is in context, data from the field "firstname" should always be visible. | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | Lisa | 2013-03-05 14:52 | 1 |  |  |  | 1
| USER EXPERIENCE: When a subject is in context, data from the field "date of birth" should always be visible. | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | Lisa | 2013-03-05 14:52 | 1 |  |  |  | 1
| USER EXPERIENCE: When a subject is in context, data from the field "subject ID" should always be visible. | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | Lisa | 2013-03-05 14:52 | 1 |  |  |  | 1
| USER EXPERIENCE: The "status" field should not automatically enter data | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | [6 empty] | 1
Wish List
| Users are able to search patients based on field in patient, collection, biospecimen - including custom fields. | [9 empty] | 1 | To do this, use the biocollection search, select the bio* and then your subject will be in context. This will be further expanded in data extraction module
| The "Patient" section of the database allows users to add test results against a patient | 1. Log in as a user with "Subject Data Manager" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Click “Study-specific Demographic Data” tab 5. Add/Edit data against he custom fields accordingly |  |  | Lisa | 2013-03-05 14:05 | 1 | this is functionality we would consider useful but which is not required for acceptance of this version |  |  | 1 | this is functionality we would consider useful but which is not required for acceptance of this version
| ability to add treatment results against a patient | 1. Log in as a user with "Subject Data Manager" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Click “Study-specific Demographic Data” tab 5. Add/Edit data against the custom fields accordingly. |  |  | Lisa | 2013-03-05 15:52 | 1 | this is functionality we would consider useful but which is not required for acceptance of this version |  |  | 1 | May also use the “Clinical Data” tab to record custom data
COLLECTIONS
New Collections
| A user with "LIMS Data Manager" access to a study can define new collections. | 1. Log in as a user with "Subject Read-Only" access to WARTN. 2. Click on the WARTN study in the Study Details tab. 3. Search for a subject, or click any of the subject links available. 4. Select a linke d sub-study to bring into context. 5. Click the “Subject Biospecimen” tab. 6. Click “New” button under the collections list. 7. Enter details as required. 8. Click “Save” | 1. The user is able to create a new collection for a subject. | 1. The user is able to create a new collection for a subject. | Lisa | 2013-03-05 14:12 | 1 |  | cellis | 2013-03-05 12:50 | 1 | new subject created successfully
| A user with "LIMS Read-Only" access to a study cannot define new collections. | 1. Log in as a user with "Subject Read-Only" access to WARTN. 2. Click on the WARTN study in the Study Details tab. 3. Search for a subject, or click any of the subject links available. 4. Select a linke d sub-study to bring into context. 5. Click the “Subject Biospecimen” tab. 6. Click “New” button under the collections list. 7. Enter details as required. 8. Click “Save” | 1. The user is unable to create a new subject. | 1. The user is unable to create a new subject. | Lisa | 2013-03-05 14:12 | 1 |  | cellis | 2013-03-05 12:50 | 1 | unable to create new subjects
Numbering
| sequential collection numbering across all studies and substudies (C-01234) | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Click “Study-specific Demographic Data” tab 5. Add/Edit data against he custom fields accordingly |  |  | Lisa | 2013-03-05 14:12 | 1 |  |  |  | 1
Wish List
Fields
| The "Collection Detail" page contains an appropriate field for entry of "study" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | [6 empty] | X | Collections are always tied to the study in context currently
| The "Collection Detail" page contains an appropriate field for entry of "substudy" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | [6 empty] | X | Collections are always tied to the study in context currently
| The "Collection Detail" page contains an appropriate field for entry of a collection "date of collection" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:12 | 1 |  |  |  | 1
| The "Collection Detail" page contains an appropriate field for entry of a collection "surgeon" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:12 | 1 |  |  |  | 1
| The "Collection Detail" page contains an appropriate field for entry of a collection "SJOG MRN" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:12 | 1 |  |  |  | 1
| The "Collection Detail" page contains an appropriate field for entry of a collection "hospital" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:12 | 1 |  |  |  | 1
| The "Collection Detail" page contains an appropriate field for entry of a collection "hospital UMRN" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:12 | 1 |  |  |  | 1
| The "Collection Detail" page contains an appropriate field for entry of a collection "study number" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:12 | 1 | Labeled StudyNo |  |  | 1
| The "Collection Detail" page contains an appropriate field for entry of a collection "path dept name (path provider)" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:24 | 1 |  |  |  | 1
| The "Collection Detail" page contains an appropriate field for entry of a collection "pathology episode number" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:24 | 1 |  |  |  | 1
| The "Collection Detail" page contains an appropriate field for entry of a collection "path histo accession number" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:24 | 1 | Accession No. | Accession No. |  | 1
| The "Collection Detail" page contains an appropriate field for entry of a collection "primary site" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:24 | 1 |  |  |  | 1
| The "Collection Detail" page contains an appropriate field for entry of a collection "histological diagnosis" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:24 | 1 |  |  |  | 1
| The "Collection Detail" page contains an appropriate field for entry of a collection "margins involved" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:24 | 1 | Involved Margins |  |  | 1
| The "Collection Detail" page contains an appropriate field for entry of a collection "lymph node involvement" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:24 | 1 |  |  |  | 1
| The "Collection Detail" page contains an appropriate field for entry of a collection "nodes sampled" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:24 | 1 |  |  |  | 1
| The "Collection Detail" page contains an appropriate field for entry of a collection "remote mets at presentation" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:24 | 1 | Field was refactored into 1st Reccurence and 2nd Recurrence |  |  | 1
| The "Collection Detail" page contains an appropriate field for entry of a collection "comments" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:24 | 1 |  |  |  | 1
| The "Collection Detail" page contains an appropriate field for entry of a collection "collection name/description" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:30 | 1 |  |  |  | 1
| A user with sufficient access can maintain study-specific and substudy specific custom fields for collections, on a per-study or per-substudy basis. | A user with sufficient access can maintain study-specific and substudy specific custom fields for collections, on a per-study or per-substudy basis. | A user with sufficient access can maintain study-specific and substudy specific custom fields for collections, on a per-study or per-substudy basis. | A user with sufficient access can maintain study-specific and substudy specific custom fields for collections, on a per-study or per-substudy basis. | [6 empty] | 1
| USER EXPERIENCE: When a study is selected (i.e. WARTN), t should be possible to see all collections and biospecimens for a subject across all substudies (except for archived substudies). | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | [6 empty] | X
| USER EXPERIENCE: When a collection is in context, a list of associated biospecimens should be accessible on every page. | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | [6 empty] | 1 | use tree to the left
| USER EXPERIENCE: When a collection is in context, the study or substudy that the collection is associated with should be readily visible. | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. |  |  |  | N/A |  |  | 1
| USER EXPERIENCE: When a collection is in context, the collection ID should always be visible, with the consent status for the assosciated substudy. | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | [6 empty] | 1
BIOSPECIMENS
| The "Biospecimen Detail" page contains an appropriate field for entry of a biospecimen "type" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:43 | 1 | Field “Sample Type: exists |  |  | 1
| The "Biospecimen Detail" page contains an appropriate field for entry of a biospecimen "behaviour" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:24 | 1 | Exists as custom field |  |  | 1
| The "Biospecimen Detail" page contains an appropriate field for entry of a biospecimen "stored in / container" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:44 | 1 |  |  |  | 1
| The "Biospecimen Detail" page contains an appropriate field for entry of a biospecimen "quantity" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:44 | 1 |  |  |  | 1
| The "Biospecimen Detail" page contains an appropriate field for entry of a biospecimen "comments" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:44 | 1 |  |  |  | 1
| The "Biospecimen Detail" page contains an appropriate field for entry of a biospecimen "sample date" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:44 | 1 |  |  |  | 1
| The "Biospecimen Detail" page contains an appropriate field for entry of a biospecimen "concentration" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:44 | 1 |  |  |  | 1
| The "Biospecimen Detail" page contains an appropriate field for entry of a biospecimen "status" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:44 | 1 |  |  |  | 1
| The "Biospecimen Detail" page contains an appropriate field for entry of a biospecimen "protocol" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:44 | 1 |  |  |  | 1
| The "Biospecimen Detail" page contains an appropriate field for entry of a biospecimen "sample time" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:44 | 1 |  |  |  | 1
| The "Biospecimen Detail" page contains an appropriate field for entry of a biospecimen "processing date" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:44 | 1 | Processing date |  |  | 1
| The "Biospecimen Detail" page contains an appropriate field for entry of a biospecimen "processing time" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:44 | 1 | Processing time |  |  | 1
| The "Biospecimen Detail" page contains an appropriate field for entry of a biospecimen "date frozen" | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-03-05 14:44 | 1 | Date Frozen custom field |  |  | 1
| A user with "Subject Read-Only" or higher access to a study can search for a biospecimen by subject ID, collection ID, or biospecimen ID, and view the "Biospecimen Details" form for a found biospecimen. | 1. Log in as a user with "Subject Read-only" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | 2. Log in as a user with "Subject Read-only" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | 3. Log in as a user with "Subject Read-only" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. |  |  |  | similar to wager. |  |  | 1 | similar to wager.
| User has the ability to print labels individually and to be batched by collection. | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | 2. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | 3. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first biospecimen in the list of biospecimens under the Subject > Biospecimen tab. 4. Click the first biospecimen in the list of biospecimens on the Subject > Subject Biospecimen page. 5. Identify that an appropriate field exists. | Lisa | 2013-03-05 14:52 | 1 |  |  |  | 1
| adding a new biospecimen can be done against a patient and then assigned to a collection - similar to wager |  |  |  | Lisa | 2013-03-05 14:52 | 1 |  |  |  | 1
| USER EXPERIENCE: When viewing the Subject > Subject Biospecimen page, the page should note the context visibly. | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | Lisa | 2013-03-05 14:52 | 1 |  |  |  | 1
| dates should default to empty - not today's date | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | Lisa | 2013-03-05 14:52 | 1 |  |  |  | 1
| this should be always visible: substudy of collection, substudy consent status, collection ID, biospecimenID, patientID, patient name | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | Lisa | 2013-03-05 14:52 | 9 | Consent status not visible, but not really a requirement |  |  | 1
| view and add transaction history for the biospecimen alongside the biospecimen data view/edit | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | Lisa | 2013-03-05 15:02 | 1 |  |  |  | 1
| process button to create child biospecimen | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | Lisa | 2013-03-05 15:02 | 1 |  |  |  | 1
| list of sub-aliquots is visible on biospecimen page | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | Lisa | 2013-03-05 15:02 | 9 | Can view tree hierarchy of biospecimens. |  |  | 1 | Tree should indicate which biospecimens have children | *
| location of a biospecimen in storage is visible on biospecimen page | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | [6 empty] | 1
| transaction history for a biospecimen always visible | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | Lisa | 2013-03-05 15:07 | 1 |  |  |  | 1