## Slide 1
NeCTAR eResearch Tools
Cloud-based Bioinformatics Tools Project
Steering Committee Meeting 27 March 2013

## Slide 2: Agenda
Project Report
  Progress against milestones
  Finance summary
  Project Risks and Issues
  External Dependencies
Other Business
Approach going forward

## Slide 3: Action items from last meeting
Action Item | Status
Paul White to investigate starting a BLOG for the project | http://thearktools.blogspot.com.au/
Paul White to establish quantitative measures by which the project’s success can be measured | Completed
Nik Zeps to discuss trial candidates with David Goldstein | Completed
Paul White and Nik Zeps to meet with chosen trial representatives in Sydney on July 4th and 5th | Completed – verbal update
Paul White to prepare a one page overview of The Ark for circulation to the projects’ collaborators. | Completed – see attached
Paul White to determine impact of AAF cost model on the project | Completed – no cost impact
Paul White to meet with Lin Fritschi to determine if there is sufficient epidemiological study representation in the set of pilot projects | TBC

## Slide 4: Project Report - Milestones
  Funding Milestone 1 – Payment received
  Funding Milestone 2 – Achieved and payment received
    Supported Tools and Processes;
    Integration with the AAF authentication services;
      Deployed in the AAF Test Environment
      Have finally received permission to use UWA’s AAF Account to move this into Production at with no ongoing charges
  Funding Milestone 3 (scheduled 31st August)
    Integrated invoicing and billing module
      Completed
    Initial Production Research Cloud Deployment (scheduled 31st August)
      LIMS, Phenotypic and Billing modules on Production NeCTAR hardware currently undergoing acceptance testing by LifePool staff using production data
      WARTN production data migrated to Production server and undergoing acceptance testing by SJOG staff

## Slide 5: Project Report - Milestones
  Funding Milestone 4 (Scheduled 30th November)
    A data extraction for analysis module;
      75% Complete – expect completion of first production release by 30th April, 2013.
    A pedigree (family) data management and visualisation module;
      20% Complete – expect completion by 10th May, 2013
  Funding Milestone 5 (Scheduled 1st March 2013)
    Enhanced reporting functionality;
      50% Complete
    Registry Management functionality for managing participant registries, such as the Australian Twin Registry
      80% Complete – was required to support SJOG data migration
    A Genotypic Data management module
      Have commenced discussions with GVL participants to determine best way to implement this

## Slide 6: Project Report - Financial
Total project budget: $614,490
Total NeCTAR contribution: $290,598
Total co-investment: $323,892
Funds received to-date $104,000
Planned EIF expenditure to 30 November $208,000
Actual EIF expenditure to-date $169,000
Planned Co-investment to 30 November $135,000
Actual Co-investment to-date $114,000

## Slide 7: NeCTAR Reporting – Risks

## Slide 8: Other Business
???????????????????????SPARL?????????????????
Date for next meeting – propose mid June, 2013.

## Slide 9: Approach Going Forward
Transparency – all projects and subcomponents will be estimated and tracked on Atlassian/JIRA.
  All participants and committee members are welcome to view progress and make feature requests
  All coders will be required to update these estimates each time they advance (or regress) in their goals/tasks
  For those seeking a less proactive view, a manually produced summary email could be sent on some regular interval (monthly or fortnightly) if required.

## Slide 10: Approach Going Forward
Prioritization – this project is already at or beyond full capacity. Feature requests are welcomed via the JIRA system. However everything will need to be prioritized.
  If we keep a good track on priorities we don’t see opportunity cost of small superficial changes add up at the cost of larger key functionality missing deadlines.
  Direct access to developers is not a recommended practice if we want priorities clear and time well managed.