## registeredUsers
| taken directly from submitted report …. | report 1 | report 2 | report 3 | report 4 | report 5 | report 6 | report 7 | report 8 | report 9
|  | number of registered users | number of registered users | number of registered users | number of registered users | number of registered users | number of registered users | number of registered users | number of registered users | number of registered users
|  | 2012-06-01 | 29-Jun-12 | 27-Jul-12 | 31-Aug-12 | 30-Nov-12 | 2013-03-31 | 2013-06-30 | 2013-09-30 | 2013-12-31
1 | Established Support Tools & Processes (Linked to Funding Milestone 2) | 5 | 5 | 5 | 5 | 5 | 15 | 35 | 60 | 61
2 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 60 | 61
3 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4
4 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | 0 | 0 | 0 | 0 | 0 | 9 | 35 | 60 | 61
5 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 55 | 56
6 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 60 | 6
8 | Implemented Registry Management Module (Linked to Funding Milestone 5) | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 60 | 61
9 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## biospecimenCounts
| taken directly from submitted report …. | report 1 | report 2 | report 3 | report 4 | report 5 | report 6 | report 7 | report 8 | report 9
|  | number of registered users | number of registered users | number of registered users | number of registered users | number of registered users | number of registered users | number of registered users | number of registered users | number of registered users
|  | 2012-06-01 | 29-Jun-12 | 27-Jul-12 | 31-Aug-12 | 30-Nov-12 | 2013-03-31 | 2013-06-30 | 2013-09-30 | 2013-12-31
1 | Established Support Tools & Processes (Linked to Funding Milestone 2)
2 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2)
3 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3)
4 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | 0 | 0 | 0 | 0 | 0 | 6 | 32290 | 46000 | 46500
5 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4)
6 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4)
7 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5)
8 | Implemented Registry Management Module (Linked to Funding Milestone 5)
9 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5)

## subjectCounts
| taken directly from submitted report …. | report 1 | report 2 | report 3 | report 4 | report 5 | report 6 | report 7 | report 8 | report 9
|  | number of registered users | number of registered users | number of registered users | number of registered users | number of registered users | number of registered users | number of registered users | number of registered users | number of registered users
|  | 2012-06-01 | 29-Jun-12 | 27-Jul-12 | 31-Aug-12 | 30-Nov-12 | 2013-03-31 | 2013-06-30 | 2013-09-30 | 2013-12-31
1 | Established Support Tools & Processes (Linked to Funding Milestone 2) | 5 | 5 | 5 | 5 | 5 | 15 | 35 | 60 | 61
2 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 60 | 61
3 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4
4 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | 0 | 0 | 0 | 0 | 0 | 6 | 32290 | 46000 | 46500
5 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 55 | 56
6 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 60 | 6
8 | Implemented Registry Management Module (Linked to Funding Milestone 5) | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 60 | 61
9 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 1
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | RED
5.Changes | GREEN
6.Dependencies
7.Measures | #REF!
8.Communications | GREEN
9.Finance | RED
Scroll up for navigation | RT029 | Cloud Based Bioinformatics Tools
| From | 2012-04-12
| To | 2012-06-01
Measures of uptake
From production infrastructure
[6 empty] | No. of registered users * |  | Average frequency of use * |  | Number of data sets uploaded * |  | Measure 4 (To be agreed) |  | Measure 5 (To be agreed) |  | Measure 6 (To be agreed)
| Service No | Service | Expected Pilot Date | Expected Production Date | Milestone No | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period
| 1 | Established Support Tools & Processes (Linked to Funding Milestone 2) | 2012-05-15 | 2012-05-15 | 3 |  | 5 |  | Daily
| 2 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | 2012-06-15 | 2012-08-15 | 5
| 3 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 7
| 4 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 8
| 5 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | 2012-09-30 | 2012-10-30 | 10
| 6 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | 2012-10-15 | 2012-11-15 | 11
| 7 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 13
| 8 | Implemented Registry Management Module (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 14
| 9 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5) | 2013-02-28 | 2013-03-30 | 15
Number of Service Levels in Exception
* Not all measures will be relevant for a particular asset. Only complete details for the appropriate measures.
See Legend

## 2
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | GREEN
5.Changes | AMBER
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
Scroll up for navigation | RT029 | Cloud Based Bioinformatics Tools
| From | 02-Jun-12
| To | 29-Jun-12
Measures of uptake
From production infrastructure
[6 empty] | No. of registered users |  | Average frequency of use |  | Number of phenotypic data sets |  | Biospecimen Counts |  | Active Studies |  | Subject Counts
| Service No | Service | Expected Pilot Date | Expected Production Date | Milestone No | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period
| 1 | Established Support Tools & Processes (Linked to Funding Milestone 2) | 2012-05-15 | 2012-05-15 | 3 | 5 | 5 | Daily | Daily | [5 empty] | 1 |  | >1000
| 2 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | 2012-06-15 | 2012-08-15 | 5
| 3 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 7
| 4 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 8
| 5 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | 2012-09-30 | 2012-10-30 | 10
| 6 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | 2012-10-15 | 2012-11-15 | 11
| 7 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 13
| 8 | Implemented Registry Management Module (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 14
| 9 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5) | 2013-02-28 | 2013-03-30 | 15
Number of Service Levels in Exception
* Not all measures will be relevant for a particular asset. Only complete details for the appropriate measures.
See Legend
1. Registered Users – The number of users which have been registered to use the system. This can be extracted using a simple SQL query against each system instance.
2. Average Use Frequency – The average frequency of use for registered users. This can be extracted using a simple SQL query against each system instance. This query would be against the user authentication logs.
3. Phenotypic Datasets – The number of phenotypic/questionnaire/clinical datasets that have been created. This can be extracted using a simple SQL query against each system instance.
4. Biospecimen Counts – The total number of physical biospecimens under management by the system. This can be extracted using a simple SQL query against each system instance.
5. Active Studies – The number of active biobanks, research studies, cohorts, registries and trials for which the system is being used. This can be extracted using a simple SQL query against each system instance.
6. Subject Counts – The number of participants/subjects for which data is being managed across the different studies. This can be extracted using a simple SQL query against each system instance.

## 3
1.Header | RED
2.Deliverables | GREEN
3.Issues | GREEN
4.Risks | GREEN
5.Changes | RED
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
Scroll up for navigation | RT029 | Cloud Based Bioinformatics Tools
| From | 30-Jun-12
| To | 27-Jul-12
Measures of uptake
From production infrastructure
[6 empty] | No. of registered users |  | Average frequency of use |  | Number of phenotypic data sets |  | Biospecimen Counts |  | Active Studies |  | Subject Counts
| Service No | Service | Expected Pilot Date | Expected Production Date | Milestone No | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period
| 1 | Established Support Tools & Processes (Linked to Funding Milestone 2) | 2012-05-15 | 2012-05-15 | 3 | 5 | 5 | Daily | Daily |  |  |  |  | 1 | 1 | >1000 | >1000
| 2 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | 2012-06-15 | 2012-08-15 | 5
| 3 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 7
| 4 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 8
| 5 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | 2012-09-30 | 2012-10-30 | 10
| 6 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | 2012-10-15 | 2012-11-15 | 11
| 7 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 13
| 8 | Implemented Registry Management Module (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 14
| 9 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5) | 2013-02-28 | 2013-03-30 | 15
Number of Service Levels in Exception
* Not all measures will be relevant for a particular asset. Only complete details for the appropriate measures.
See Legend
1. Registered Users – The number of users which have been registered to use the system. This can be extracted using a simple SQL query against each system instance.
2. Average Use Frequency – The average frequency of use for registered users. This can be extracted using a simple SQL query against each system instance. This query would be against the user authentication logs.
3. Phenotypic Datasets – The number of phenotypic/questionnaire/clinical datasets that have been created. This can be extracted using a simple SQL query against each system instance.
4. Biospecimen Counts – The total number of physical biospecimens under management by the system. This can be extracted using a simple SQL query against each system instance.
5. Active Studies – The number of active biobanks, research studies, cohorts, registries and trials for which the system is being used. This can be extracted using a simple SQL query against each system instance.
6. Subject Counts – The number of participants/subjects for which data is being managed across the different studies. This can be extracted using a simple SQL query against each system instance.

## 4
1.Header | RED
2.Deliverables | AMBER
3.Issues | GREEN
4.Risks | GREEN
5.Changes | RED
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | RED
Scroll up for navigation | RT029 | Cloud Based Bioinformatics Tools
| From | 28-Jul-12
| To | 31-Aug-12
Measures of uptake
From production infrastructure
[6 empty] | No. of registered users |  | Average frequency of use |  | Number of phenotypic data sets |  | Biospecimen Counts |  | Active Studies |  | Subject Counts
| Service No | Service | Expected Pilot Date | Expected Production Date | Milestone No | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period
| 1 | Established Support Tools & Processes (Linked to Funding Milestone 2) | 2012-05-15 | 2012-05-15 | 3 | 5 | 5 | Daily | [5 empty] | 1 |  | >1000
| 2 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | 2012-06-15 | 2012-08-15 | 5
| 3 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 7
| 4 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 8
| 5 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | 2012-09-30 | 2012-10-30 | 10
| 6 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | 2012-10-15 | 2012-11-15 | 11
| 7 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 13
| 8 | Implemented Registry Management Module (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 14
| 9 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5) | 2013-02-28 | 2013-03-30 | 15
Number of Service Levels in Exception
* Not all measures will be relevant for a particular asset. Only complete details for the appropriate measures.
See Legend
1. Registered Users – The number of users which have been registered to use the system. This can be extracted using a simple SQL query against each system instance.
2. Average Use Frequency – The average frequency of use for registered users. This can be extracted using a simple SQL query against each system instance. This query would be against the user authentication logs.
3. Phenotypic Datasets – The number of phenotypic/questionnaire/clinical datasets that have been created. This can be extracted using a simple SQL query against each system instance.
4. Biospecimen Counts – The total number of physical biospecimens under management by the system. This can be extracted using a simple SQL query against each system instance.
5. Active Studies – The number of active biobanks, research studies, cohorts, registries and trials for which the system is being used. This can be extracted using a simple SQL query against each system instance.
6. Subject Counts – The number of participants/subjects for which data is being managed across the different studies. This can be extracted using a simple SQL query against each system instance.

## 5
1.Header | RED
2.Deliverables | RED
3.Issues | GREEN
4.Risks | GREEN
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | AMBER
Scroll up for navigation | RT029 | Cloud Based Bioinformatics Tools
| From | 01-Sep-12
| To | 30-Nov-12
Measures of uptake
From production infrastructure
[6 empty] | No. of registered users |  | Average frequency of use |  | Number of phenotypic data sets |  | Biospecimen Counts |  | Active Studies |  | Subject Counts
| Service No | Service | Expected Pilot Date | Expected Production Date | Milestone No | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period
| 1 | Established Support Tools & Processes (Linked to Funding Milestone 2) | 2012-05-15 | 2012-05-15 | 3 |  | 5 |  | Daily | [7 empty] | 25000
| 2 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | 2012-06-15 | 2012-08-15 | 5
| 3 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 7
| 4 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 8
| 5 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | 2012-09-30 | 2012-10-30 | 10
| 6 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | 2012-10-15 | 2012-11-15 | 11
| 7 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 13
| 8 | Implemented Registry Management Module (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 14
| 9 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5) | 2013-02-28 | 2013-03-30 | 15
Number of Service Levels in Exception
* Not all measures will be relevant for a particular asset. Only complete details for the appropriate measures.
See Legend
1. Registered Users – The number of users which have been registered to use the system. This can be extracted using a simple SQL query against each system instance.
2. Average Use Frequency – The average frequency of use for registered users. This can be extracted using a simple SQL query against each system instance. This query would be against the user authentication logs.
3. Phenotypic Datasets – The number of phenotypic/questionnaire/clinical datasets that have been created. This can be extracted using a simple SQL query against each system instance.
4. Biospecimen Counts – The total number of physical biospecimens under management by the system. This can be extracted using a simple SQL query against each system instance.
5. Active Studies – The number of active biobanks, research studies, cohorts, registries and trials for which the system is being used. This can be extracted using a simple SQL query against each system instance.
6. Subject Counts – The number of participants/subjects for which data is being managed across the different studies. This can be extracted using a simple SQL query against each system instance.

## 6
1.Header | AMBER
2.Deliverables | RED
3.Issues | GREEN
4.Risks | GREEN
5.Changes | AMBER
6.Dependencies
7.Measures
8.Communications | GREEN
9.Finance | GREEN
Scroll up for navigation | RT029 | Cloud Based Bioinformatics Tools
| From | 2012-12-01
| To | 2013-03-31
Measures of uptake
From production infrastructure
[6 empty] | No. of registered users |  | Average frequency of use |  | Number of phenotypic data sets |  | Biospecimen Counts |  | Active Studies |  | Subject Counts
| Service No | Service | Expected Pilot Date | Expected Production Date | Milestone No | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period
| 1 | Established Support Tools & Processes (Linked to Funding Milestone 2) | 2012-05-15 | 2012-05-15 | 3 | 5 | 15 | Daily | Daily | [5 empty] | 1 | 25000 | 32500
| 2 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | 2012-06-15 | 2012-08-15 | 5 |  | 0 |  | Daily
| 3 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 7 |  | 0 |  | Daily
| 4 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 8 |  | 9 |  | Daily |  |  |  | 6 |  | 2
| 5 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | 2012-09-30 | 2012-10-30 | 10
| 6 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | 2012-10-15 | 2012-11-15 | 11
| 7 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 13
| 8 | Implemented Registry Management Module (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 14 |  |  |  | Daily
| 9 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5) | 2013-02-28 | 2013-03-30 | 15
Number of Service Levels in Exception
* Not all measures will be relevant for a particular asset. Only complete details for the appropriate measures.
See Legend
1. Registered Users – The number of users which have been registered to use the system. This can be extracted using a simple SQL query against each system instance.
2. Average Use Frequency – The average frequency of use for registered users. This can be extracted using a simple SQL query against each system instance. This query would be against the user authentication logs.
3. Phenotypic Datasets – The number of phenotypic/questionnaire/clinical datasets that have been created. This can be extracted using a simple SQL query against each system instance.
4. Biospecimen Counts – The total number of physical biospecimens under management by the system. This can be extracted using a simple SQL query against each system instance.
5. Active Studies – The number of active biobanks, research studies, cohorts, registries and trials for which the system is being used. This can be extracted using a simple SQL query against each system instance.
6. Subject Counts – The number of participants/subjects for which data is being managed across the different studies. This can be extracted using a simple SQL query against each system instance.

## 7
1.Header | AMBER
2.Deliverables | RED
3.Issues | GREEN
4.Risks | GREEN
5.Changes | RED
6.Dependencies
7.Measures
8.Communications | AMBER
9.Finance | GREEN
Scroll up for navigation | RT029 | Cloud Based Bioinformatics Tools
| From | 2013-04-01
| To | 2013-06-30
Measures of uptake
From production infrastructure
[6 empty] | No. of registered users |  | Average frequency of use |  | Number of phenotypic data sets |  | Biospecimen Counts |  | Active Studies |  | Subject Counts
| Service No | Service | Expected Pilot Date | Expected Production Date | Milestone No | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period
| 1 | Established Support Tools & Processes (Linked to Funding Milestone 2) | 2012-05-15 | 2012-05-15 | 3 | 15 | 35 | Daily | daily |  |  |  |  | 1 | 25 | 32500 | 45000
| 2 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | 2012-06-15 | 2012-08-15 | 5 | 0 | 35 | Daily | daily
| 3 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 7 | 0 | 4 | Daily | daily
| 4 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 8 | 9 | 35 | Daily | daily |  | 4 | 6 | 32290 | 2 | 29
| 5 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | 2012-09-30 | 2012-10-30 | 10 |  | 35 |  | daily
| 6 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | 2012-10-15 | 2012-11-15 | 11
| 7 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 13 |  | 35 |  | daily
| 8 | Implemented Registry Management Module (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 14 |  | 35 | Daily | daily
| 9 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5) | 2013-02-28 | 2013-03-30 | 15
Number of Service Levels in Exception
* Not all measures will be relevant for a particular asset. Only complete details for the appropriate measures.
See Legend
1. Registered Users – The number of users which have been registered to use the system. This can be extracted using a simple SQL query against each system instance.
2. Average Use Frequency – The average frequency of use for registered users. This can be extracted using a simple SQL query against each system instance. This query would be against the user authentication logs.
3. Phenotypic Datasets – The number of phenotypic/questionnaire/clinical datasets that have been created. This can be extracted using a simple SQL query against each system instance.
4. Biospecimen Counts – The total number of physical biospecimens under management by the system. This can be extracted using a simple SQL query against each system instance.
5. Active Studies – The number of active biobanks, research studies, cohorts, registries and trials for which the system is being used. This can be extracted using a simple SQL query against each system instance.
6. Subject Counts – The number of participants/subjects for which data is being managed across the different studies. This can be extracted using a simple SQL query against each system instance.

## 8
1.Header | AMBER
2.Deliverables | RED
3.Issues | GREEN
4.Risks | GREEN
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | AMBER
9.Finance | GREEN
Scroll up for navigation | RT029 | Cloud Based Bioinformatics Tools
| From | 2013-07-01
| To | 2013-09-30
Measures of uptake
From production infrastructure
[6 empty] | No. of registered users |  | Average frequency of use |  | Number of phenotypic data sets |  | Biospecimen Counts |  | Active Studies |  | Subject Counts
| Service No | Service | Expected Pilot Date | Expected Production Date | Milestone No | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period
| 1 | Established Support Tools & Processes (Linked to Funding Milestone 2) | 2012-05-15 | 2012-05-15 | 3 | 35 | 60 | daily | daily |  |  |  |  | 25 | 25 | 45000
| 2 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | 2012-06-15 | 2012-08-15 | 5 | 35 | 60 | daily | daily
| 3 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 7 | 4 | 4 | daily | daily
| 4 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 8 | 35 | 60 | daily | daily | 4 | 4 | 32290 | 46000 | 29 | 29
| 5 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | 2012-09-30 | 2012-10-30 | 10 | 35 | 55 | daily | daily
| 6 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | 2012-10-15 | 2012-11-15 | 11
| 7 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 13 | 35 | 60 | daily | daily
| 8 | Implemented Registry Management Module (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 14 | 35 | 60 | daily | daily
| 9 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5) | 2013-02-28 | 2013-03-30 | 15
Number of Service Levels in Exception
* Not all measures will be relevant for a particular asset. Only complete details for the appropriate measures.
See Legend
1. Registered Users – The number of users which have been registered to use the system. This can be extracted using a simple SQL query against each system instance.
2. Average Use Frequency – The average frequency of use for registered users. This can be extracted using a simple SQL query against each system instance. This query would be against the user authentication logs.
3. Phenotypic Datasets – The number of phenotypic/questionnaire/clinical datasets that have been created. This can be extracted using a simple SQL query against each system instance.
4. Biospecimen Counts – The total number of physical biospecimens under management by the system. This can be extracted using a simple SQL query against each system instance.
5. Active Studies – The number of active biobanks, research studies, cohorts, registries and trials for which the system is being used. This can be extracted using a simple SQL query against each system instance.
6. Subject Counts – The number of participants/subjects for which data is being managed across the different studies. This can be extracted using a simple SQL query against each system instance.

## 9
1.Header | AMBER
2.Deliverables | RED
3.Issues | GREEN
4.Risks | GREEN
5.Changes | GREEN
6.Dependencies
7.Measures
8.Communications | AMBER
9.Finance | GREEN
Scroll up for navigation | RT029 | Cloud Based Bioinformatics Tools
| From | 2013-10-01
| To | 2013-12-31
Measures of uptake
From production infrastructure
[6 empty] | No. of registered users |  | Average frequency of use |  | Number of phenotypic data sets |  | Biospecimen Counts |  | Active Studies |  | Subject Counts
| Service No | Service | Expected Pilot Date | Expected Production Date | Milestone No | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period | Last period | This period
| 1 | Established Support Tools & Processes (Linked to Funding Milestone 2) | 2012-05-15 | 2012-05-15 | 3 | 60 | 61 | daily | daily |  |  |  |  | 25 | 29
| 2 | Integrated existing application with AAF Authentication Services (Linked to Funding Milestone 2) | 2012-06-15 | 2012-08-15 | 5 | 60 | 61 | daily | daily
| 3 | Integrated Invoicing & Billing Complete (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 7 | 4 | 4 | daily | daily
| 4 | Initial Production Research Cloud Deployed (Linked to Funding Milestone 3) | 2012-08-15 | 2012-09-15 | 8 | 60 | 61 | daily | daily | 4 | 9 | 46000 | 46500 | 29 | 29 |  | 55000
| 5 | Implemented Data Extraction for Analysis Module (Linked to Funding Milestone 4) | 2012-09-30 | 2012-10-30 | 10 | 55 | 56 | daily | daily
| 6 | Implemented Pedigree Storage & Visualisation Module (Linked to Funding Milestone 4) | 2012-10-15 | 2012-11-15 | 11
| 7 | Enhanced Data Linkage & Reporting Module Complete (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 13 | 60 | 6 | daily | daily
| 8 | Implemented Registry Management Module (Linked to Funding Milestone 5) | 2012-12-15 | 2013-01-30 | 14 | 60 | 61 | daily | daily
| 9 | Integrated Genotypic Data Management Capability (Linked to Funding Milestone 5) | 2013-02-28 | 2013-03-30 | 15 |  | 0
Number of Service Levels in Exception
* Not all measures will be relevant for a particular asset. Only complete details for the appropriate measures.
See Legend
1. Registered Users – The number of users which have been registered to use the system. This can be extracted using a simple SQL query against each system instance.
2. Average Use Frequency – The average frequency of use for registered users. This can be extracted using a simple SQL query against each system instance. This query would be against the user authentication logs.
3. Phenotypic Datasets – The number of phenotypic/questionnaire/clinical datasets that have been created. This can be extracted using a simple SQL query against each system instance.
4. Biospecimen Counts – The total number of physical biospecimens under management by the system. This can be extracted using a simple SQL query against each system instance.
5. Active Studies – The number of active biobanks, research studies, cohorts, registries and trials for which the system is being used. This can be extracted using a simple SQL query against each system instance.
6. Subject Counts – The number of participants/subjects for which data is being managed across the different studies. This can be extracted using a simple SQL query against each system instance.