## Finance 2
| 1.Header | AMBER
| 2.Deliverables | RED
| 3.Issues | GREEN
| 4.Risks | GREEN
| 5.Changes | GREEN
6.Dependencies
7.Measures
| 8.Communications | GREEN
| 9.Finance | GREEN
|  | RT029 | Cloud Based Bioinformatics Tools
|  | From | 2012-12-01
|  | To | 2013-03-01
|  | Finance | [5 empty] | STATUS | GREEN
|  |  |  | Approved Nectar Funds |  |  |  |  | Approved Co-investment
|  | FOR YOUR INFORMATION |  | Total Approved Nectar Funds | Actual Nectar Funds PAID to Project | Actual Project Expenditure Reported | Estimated Cost to complete | Nectar Cash Flow amount to be allocated | Total Approved Co-investment Funds | Actual Co-investment and in-Kind Expenditure Reported | Estimated Co-investment to Complete
|  |  |  | 289000 | 104000 | 152482 | 185000 | 0 | 323892 | 102384 | 221508
[13 empty] | This column holds the values to put in the warning box in row 40 |  |  |  |  | FinanceLight Element | Status
Financial Reporting Period ID | Financial Reporting Period |  | Nectar Funds RECEIVED | Expenditure: Actual Nectar Funds |  |  |  | Project Manager's Nectar Funds FORECAST | Expenditure: Actual Co-investment |  |  | Project Manager's Co-investment FORECAST |  |  | Estimated Project Cash Flow EIF - Shows Actuals where available | Project Manager's Estimated Project Cash Flow Co-investment |  | PM estimate = EIF Allocated | Correct 289000 = 289000 | Total Project Manager's Nectar and Co-investment ACTUAL and FORECASTED Expenditure
| Start Date | End Date |  | Personnel | Equipment | Other | Total |  | Cash Contribution | In-Kind Contribution | Total | [6 empty] | 30% of funds | 86700
1 | 2012-07-01 | 2012-12-31 | 104000 | 122279 | 0 |  | 122279 | 122279 | 2364 | 72474 | 74838 | 74838 |  |  | 122279 | 74838 |  | 30% of funds or more in last quarter | Less than 30% of funds in last quarter: 15552 | 197117
2 | 2013-01-01 | 2013-03-31 |  | 30203 |  |  | 30203 | 30203 |  | 9910 | 9910 | 9910 |  |  | 30203 | 9910 |  | Last Quarter | 15552 | 40113
3 | 2013-04-01 | 2013-06-30 |  |  |  |  | 0 | 60141 | 6000 |  | 6000 | 2825 |  |  | 60141 | 6000 |  | 20% of funds | 57800 | 62966
4 | 2013-07-01 | 2013-09-30 |  |  |  |  | 0 | 60825 | 6000 |  | 6000 | 16637 |  |  | 60825 | 6000 |  | 20% of funds or more in last quarter | Less than 20% of funds in last quarter: 15552 | 77462
5 | 2013-10-01 | 2013-12-31 |  |  |  |  | 0 | 15552 | 5636 |  | 5636 | 4927 |  |  | 15552 | 5636 |  | FINANCE LIGHT | GREEN | 20479
6 | 2014-01-01 | 2014-03-31 |  |  |  |  | 0 | 0 |  |  | 0 | 110637 |  |  | 0 | 110637 |  |  |  | 110637
7 | 2014-04-01 | 2014-06-30 |  |  |  |  | 0 | 0 |  |  | 0 | 110638 |  |  | 0 | 110638 |  |  |  | 110638
8 | 2014-07-01 | 2014-09-30 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
9 | 2014-10-01 | 2014-12-31 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
10 | 2015-01-01 | 2015-03-31 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
11 | 2015-04-01 | 2015-06-30 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
12 | 2015-07-01 | 2015-09-30 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
13 | 2015-10-01 | 2015-12-31 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0
|  | TOTAL | 104000 | 152482 | 0 | 0 | 152482 | 289000 | 20000 | 82384 | 102384 | 330412 |  |  | 289000 | 323659
[7 empty] | Nectar Allocated | 289000
Optional Comment
|  |  |  | 2012-12-31 | 2013-03-31 | 2013-06-30 | 2013-09-30 | 2013-12-31 | 2014-03-31 | 2014-06-30 | 2014-09-30 | 2014-12-31 | 2015-03-31 | 2015-06-30 | 2015-09-30 | 2015-12-31 | Total
|  | Nectar Proposal Budget |  | 208000 | 260000 | 260000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000
|  | PM Nectar Forecast |  | 122279 | 30203 | 60141 | 60825 | 15552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289000
|  | PM Nectar Forecast (Accum) |  | 122279 | 152482 | 212623 | 273448 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000 | 289000
|  | Nectar Actual |  | 122279 | 30203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152482
|  | Nectar Actual (Accum) |  | 122279 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 152482
|  | Nectar Paid (Accum) |  | 104000 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 104000
|  | Co Inv Proposal Budget |  | 66426 | 114892 | 323892 | 323892 | 323892 | 323892 | 323892 | 323892 | 323892 | 323892 | 323892 | 323892 | 323892 | 323892
|  | PM Co inv Forecast |  | 74838 | 9910 | 2825 | 16637 | 4927 | 110637 | 110638 | 0 | 0 | 0 | 0 | 0 | 0 | 330412
|  | PM Co inv Forecast (Accum) |  | 74838 | 84748 | 87573 | 104210 | 109137 | 219774 | 330412 | 330412 | 330412 | 330412 | 330412 | 330412 | 330412 | 102384
|  | Co Inv Actuals |  | 74838 | 9910 | 6000 | 6000 | 5636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102384
|  | Co Inv Actuals (Accum) |  | 74838 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 102384
Note on O19: mecolesm: TO setup the sheet: OPTIONAL A. Modify dates B25-B37 as required. ONLY IF A. CHANGED B. Change named cell "LASTQUARTER" which is currently in H29 if dates are modified above. If the last quarter is modified, then this needs to reflect the new last quarter. (LASTQUARTER is used in the status lights. See columns R and S) ESSENTIAL 1. Add baseline amounts to row 44 and row 50. 2. HIDE rows 43-55 3. HIDE columns M-S 4. Protect Sheet (no password, allow select locked cells; select unlocked cells.) DONE *NOTE the #N/A in rows 48,49,54 are to remove dates not yet passed (based on the end date of the report) from showing in the graphs. They are not errors.

## Sheet1
Milestone | Associated Deliverable Start Date | Milestone Date | EIF Funding | Co-investment Funding |  | Cumulative Expenditure to 1 Dec 12 |  |  | Dec-March |  |  | March-May |  |  | May-August |  |  | Aug-Nov
Sub-contract signed |  | 2012-01-31 |  |  | 2012-12-01 |  |  | 2013-03-31 |  |  | 2013-06-30 |  |  | 2013-09-30 |  |  | 2013-12-31
Funding Milestone 1 |  | 2012-03-31 | 55000 |  |  | nectar | co-inv |  | nectar | co-inv |  | nectar | co-inv |  | nectar | co-inv |  | nectar | co-inv
Established Support Tools & Processes | 2012-03-01 | 2012-03-15 | 6944 | 406 | 100% | 6944 | 406 | 100% | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 0
Funding Milestone 2 |  | 2012-03-31 | 55000 | [8 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0
Integrated existing application with AAF Authentication Services | 2012-03-15 | 2012-04-30 | 20833 | 3331 | 100% | 20833 | 3331 | 100% | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 0
Integrated Invoicing & Billing | 2012-03-01 | 2012-06-30 | 14605 | 40163 | 100% | 14605 | 40163 | 100% | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 0
Initial Production Research Cloud Deployed | 2012-03-01 | 2012-06-30 | 46911 | 9462 | 75% | 35183.25 | 7096.5 | 100% | 11727.75 | 2365.5 | 100% | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 0
Funding Milestone 3 |  | 2012-06-30 | 55000 | [8 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0
Implemented Data Extraction for Analysis Module | 2012-06-15 | 2012-08-15 | 26680 | 1420 | 50% | 13340 | 710 | 75% | 6670 | 355 | 100% | 6670 | 355 | 100% | 0 | 0 | 100% | 0 | 0
Implemented Pedigree Storage & Visualisation Module | 2012-05-01 | 2012-08-30 | 58800 | 11645 | 25% | 14700 | 2911.25 | 25% | 0 | 0 | 100% | 44100 | 8733.75 | 100% | 0 | 0 | 100% | 0 | 0
Funding Milestone 4 |  | 2012-09-30 | 55000 | [8 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0
Enhanced Data Linkage & Reporting Module | 2012-09-01 | 2012-11-30 | 37485 | 7424 | 25% | 9371.25 | 1856 | 50% | 9371.25 | 1856 | 75% | 9371.25 | 1856 | 100% | 9371.25 | 1856 | 100% | 0 | 0
Implemented Registry Management Module | 2012-07-01 | 2012-11-30 | 9736 | 21334 | 75% | 7302 | 16000.5 | 100% | 2434 | 5333.5 | 100% | 0 | 0 | 100% | 0 | 0 | 100% | 0 | 0
Integrated Genotypic Data Management Capability | 2012-08-15 | 2012-12-31 | 68605 | 19708 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 75% | 51453.75 | 14781 | 100% | 17151.25 | 4927
Funding Milestone 5 |  | 2012-12-31 | 55000 | [14 empty] | however giving 15552 in order to deal with nectars reduced funding
Funding Milestone 6 - Final Admin Closure |  | 2013-09-30 | 31000
System Support | 2013-01-01 | 2014-06-30 |  | 189000
Travel Budget (UWA Centre for Genetic Epidemiology and Biostatistics) |  |  |  | 10000 |  |  | 2364
Other Expenses (UWA Research Matching Funds) |  |  |  | 10000
Total EIF Request |  |  | 290598 |  |  | 122278.5 | 74838.25 |  | 30203 | 9910 |  | 60141.25 | 10944.75 |  | 60825 | 16637 |  | 17151.25 | 4927
[5 empty] | Cumulative |  |  |  | 152481.5 | 84748.25 |  | 212622.75 | 95693 |  | 273447.75 | 112330 |  | 290599 | 117257
[5 empty] | total combined? |  | 197116.75 |  |  | 237229.75 |  |  | 308315.75 |  |  | 385777.75 |  |  | 407856
323893
[9 empty] | 102617 | 323892 | 221275 |  |  | 206635 |  |  | 290599
[11 empty] | 110637.5 |  |  | 103317.5
84747.75
42373.875