## UAT Items List
Result coding: 1 = Pass (full functionality with no unexpected errors), 0 = Fail (lack of required functionality or reproducible error during testing), 9 = Conditional (partial functionality, error during testing which cannot be reproduced, poor user experience or other constraints) X = Functionality which is desirable for future iterations of the system. these items are not necessary for user acceptance of this version of the system
# | Test description | Test Protocol | Pass (all items) | Fail (on any item) | User | Test time | Result | Notes
2 | STUDIES
2.1 | New Studies
2.1.1 | A user with "Study Administrator" access to a study can define new substudies. | 1. Log in as a user with "Study Administrator" access to WARTN. 2. Click on the WARTN study in the Study Details tab. 3. Click the "New Child Study" button. 4. Enter relevant data for required fields marked with an asterisk and click the "Save" button. | 1. The user is able to create the new substudy. 2. The new substudy is recognised as a child study of WARTN. | 1. The user is unable to create the new substudy. 2. The new substudy is not recognised as a child study of WARTN. | Lisa | 2013-08-07 11:55 | 1
2.1.2 | A user with "Study Read-Only" access to a study cannot define new substudies. | 1. Log in as a user with "Study Read Only" access to WARTN, 2. Click on the WARTN study in the Study Details tab. 3. Click the "New Child Study" button, 4. Enter relevant data for required fields marked with an asterisk, and click the "Save" button. | 1. The user is unable to create the new substudy. | 1. The user is able to create the new substudy. | Lisa | 2013-08-07 11:29 | 1
2.1.3 | The "Study Administrator" who creates a new substudy gains full Administrative rights to that substudy on its creation. | 1. Log in as a user with "Study Administrator" access to WARTN. 2. Click on the WARTN study in the Study Details tab. 3. Click the "New Child Study" button. 4. Enter relevant date for required fields marked with an asterisk and click the "Save" button. 5. In the Study > Manage Users tab, search for the applicable user from the context of WARTN. 6. In the Study > Manage Users tab, search for the applicable user from the context of the new substudy. 7. Compare the access rights between the two. | 1. The user is able to be located under "Manage Users". 2. The user's access rights for the new substudy are the same as their access rights for the WARTN study. | 1. The user is unable to be located under "Manage Users". 2. The user's access rights for the new substudy are different to their access rights for the WARTN study. | Lisa | 2013-08-07 11:58 | 1
2.2 | Numbering / IDs.
2.2.2 | On creation of a study, a user with "Study Administrator" access can set the system of collection IDs for a study and all of its substudies. | On creation of a study, a user with "Study Administrator" access can set the system of collection IDs for a study and all of its substudies. | 1. The user is able to set the system of collection IDs for a study and all of its sub-studies | 1. The user is unable to set the sysem of collection IDs for a study and all of its substudies | Lisa | 2013-08-07 11:00 | 1
2.2.4 | On creation of a study, a user with "Study Administrator" access can select for a study to generate sequential subject IDs across all substudies it contains. | On creation of a study, a user with "Study Administrator" access can select for a study to generate sequential subject IDs across all substudies it contains. | 1. The user is able to set subject IDs to be sequential across all substudies. | 1. The user is unable to set subject IDs to be sequential across all substudies. | Lisa | 2013-08-07 11:10 | 1
2.2.5 | On creation of a study, a user with "Study Administrator" access can select for a study to generate sequential collection IDs across all substudies it contains. | On creation of a study, a user with "Study Administrator" access can select for a study to generate sequential collection IDs across all substudies it contains. | 1. The user is able to set collection IDs to be sequential across all substudies. | 1. The user is unable to set collection IDs to be sequential across all substudies. | Lisa | 2013-08-07 11:12 | 1
2.2.6 | On creation of a study, a user with "Study Administrator" access can select for a study to generate sequential biospecimen IDs across all substudies it contains. | On creation of a study, a user with "Study Administrator" access can select for a study to generate sequential biospecimen IDs across all substudies it contains. | 1. The user is able to set biospecimen IDs to be sequential across all substudies. | 1. The user is unable to set biospecimen IDs to be sequential across all substudies. | Lisa | 2013-08-07 11:13 | 1
2.3 | Sub-study access
2.3.1 | A user with "Study Administrator" access to a study and all of its substudies can modify user access to a specific substudy without altering their access to the parent study. | 1. Select a substudy in the Study > Study Details tab. 2. In the Study > Manage Users tab, select a user with "Study Read-Only" access to WARTN and all substudies, and modify their access to the selected substudy. 3. Log out of the Ark and log back in as the selected user. 4. Check that the access to WARTN is independent to the changes to the substudy. 5. Check that the access to other substudies is independent to the changes to the substudy. 6. Check that the access to the target substudy is changed. 7. Repeat steps 2 to 6 for a user without Study Read-Only access to the WARTN study or any of it's substudies. | 1. Study Administrator is able to modify substudy specific access for users with access to WARTN. 2. The modified user is able to confirm the appropriate access changes. 3. The user's access to WARTN is unaffected by substudy access modifications. 4. The user's access to a substudy is not governed by WARTN access. 5. Substudy access modifications do not affect the user's access to WARTN. 6. Substudy access modifications do not affect the user's access to other substudies. | 1. Study Administrator is unable to modify substudy specific access for users with access to WARTN. 2. The modified user is unable to confirm the appropriate access changes. 3. The user's access to WARTN is affected by substudy access modifications. 4. The user's access to a substudy is governed by WARTN access. 5. Substudy access modifications affect the user's access to WARTN. 6. Substudy access modifications affect the user's access to other substudies. | Lisa | in discussion, propsed change | 9 | ARK-1042
2.3.2 | A user with "Study Read-Only" access to a study and all of its substudies cannot modify user access to a study or substudy | 1. Select a substudy in the Study > Study Details tab. 2. In the Study > Manage Users tab, select a user with "Study Read-Only" access to WARTN and all substudies, and modify their access to the selected substudy. 3. Log out of the Ark and log back in as the selected user. 4. Check that the access to WARTN is unchanged. 5. Check that the access to other substudies is unchanged. 6. Check that the access to the target substudy is unchanged. | 1. User is unable to modify study or substudy specific access for other users 2. The modified user's access to the target substudy is unchanged 3. The modified user's access to WARTN is unchanged. 4. The modified user's access to other substudies is unchanged. | 1. User is able to modify study or substudy specific access for other users 2. The modified user's access to the target substudy has changed 3. The modified user's access to WARTN has changed. 4. The modified user's access to other substudies has changed. | Lisa | 2013-08-07 11:30 | 1
2.3.3 | A user with access rights to a study cannot access a substudy for which they do not have access. | 1. Log in as a user with "Study Administrator" access to WARTN. 2. Select a substudy in the Study > Study Details tab. 3. In the Study > Manage Users tab, select a user with access to WARTN and the previously selected substudy, and remove their access to the substudy. 4. Log out of the Ark and log back in as the selected user. 5. Check for access to WARTN. 6. Check for access to the selected substudy. 7. Check for access to other substudies. | 1. A Study Administrator is able to remove access to a substudy for users with access to WARTN. 2 The modified user is unable to see a substudy for which they do not have access. 3. The user is unable to identify patients, collections, biospecimens, transactions, and freezer allocations associated with a substudy for which they do not have access. 4. The user's access to WARTN is unaffected by substudy access modifications. 5. The user's access to a substudy is not governed by WARTN access. 6. Substudy access modifications do not affect the user's access to WARTN. 7. Substudy access modifications do not affect the user's access to other substudies. | 1. A Study Administrator is able to remove access to a substudy for users with access to WARTN. 2 The modified user is unable to see a substudy for which they do not have access. 3. The user is able to identify patients, collections, biospecimens, transactions, or freezer allocations associated with a substudy for which they do not have access. 4. The user's access to WARTN is affected by substudy access modifications. 5. The user's access to a substudy is governed by WARTN access. 6. Substudy access modifications affect the user's access to WARTN. 7. Substudy access modifications affect the user's access to other substudies. | Lisa |  | 9 | ARK-1042
2.4 | Archiving
2.4.1 | A user with "Study Read-Only" access to a study and all of its substudies cannot set a study or substudy as "archived" | 1. Log in as a user with "Study Read-Only" access to WARTN and all of its substudies. 2. Click on a WARTN substudy in the Study Details tab. 3. Alter the "Status" of the study to "Archived", and click the "Save" button. | 1. The user is able to see a list of all studies and substudies. 2. The user is able to view the study details. 3. The user is unable to modify study details. 4. The user is unable to set the substudy's status to "Archived". | 1. The user is unable to see a list of all studies and substudies. 2. The user is unable to view the study details. 3. The user is able to modify study details. 4. The user is able to set the substudy's status to "Archived". | Lisa | 2013-08-07 12:50 | 1
2.4.2 | A user with "Study Administrator" access to a study and all of its substudies can set a study or substudy as "Archived". | 1. Log in as a user with "Study Administrator" access to WARTN and all of its substudies. 2. Click on a WARTN substudy in the Study Details tab. 3. Alter the "Status" of the study to "Archived", and click the "Save" button. | 1. The user is able to see a list of all studies and substudies. 2. The user is able to view the study details. 3. The user is able to modify study details. 4. The user is able to set the substudy's status to "Archived". | 1. The user is unable to see a list of all studies and substudies. 2. The user is unable to view the study details. 3. The user is unable to modify study details. 4. The user is unable to set the substudy's status to "Archived". | Lisa | 2013-08-07 11:38 | 1
2.4.4 | A user with "Study Read-Only" access to a study and all of its substudies cannot view any archived substudies in the Study > Study Details tab. | 1. Log in as a user with "Study Read-Only" access to WARTN and all of its substudies. 2. Identify an archived substudy in the Study > Study Details tab. 3. Identify that the study is Archived. | 1. The user is unable identify archived substudies in the Study > Study Details tab. 2. The user is able to identify active studies in the Study > Study Details tab. | 1. The user is able to identify the archived substudy in the Study > Study Details tab. 2. The user is unable to identify active studies in the Study > Study Details tab. | Lisa | 2013-08-07 12:52 | 1
2.4.5 | A user with access to a study and all of its substudies cannot identify Archived substudies in the "Study" value list in the Subject > Demographic Data tab. | 1. Log in as a user with access to WARTN and all of its substudies. 2. Under Study > Study Details, enter the context of the WARTN study. 3. In the Subject > Demographic Data tab, find the name of an archived substudy in the "Study" value list. | 1. The user is able to view the Subject > Demographic Data tab from the context of the WARTN study. 2. The user is unable to identify the archived study in the Subject > Demographic Data "Study" value list. 3. The user is able to identify all active substudies in the Subject > Demographic Data "Study" value list. | 1. The user is unable to view the Subject > Demographic Data tab from the context of the WARTN study. 2. The user is able to identify the archived study in the Subject > Demographic Data "Study" value list. 3. The user is unable to identify all active substudies in the Subject > Demographic Data "Study" value list. | Lisa | 2013-08-07 11:40 | 1
2.4.6 | A user with access to a study and all of its substudies cannot identify the patients, transactions, or biospecimens associated with archived substudies from within the Subject > Demographic Data tab. | 1. Log in as a user with access to WARTN and all of its substudies. 2. Under Study > Study Details, enter the context of the WARTN study. 3. In the Subject > Demographic Data tab, find a patient with a known association to an active substudy and an archived substudy. 4. Attempt to identify which substudies the patient is associated with. | 1. The user is able to view the Subject > Demographic Data tab from the context of the WARTN study. 2. The user is unable to identify patients assigned to the archived study. 3. The user is able to identify all patients assigned to all active studies. | 1. The user is unable to view the Subject > Demographic Data tab from the context of the WARTN study. 2. The user is able to identify patients assigned to the archived study. 3. The user is unable to identify all patients assigned to all active studies. | Lisa | 2013-08-07 11:55 | 1 | Can not see achived study in Demographic Data page dropdown and can not see it on the Study Detail page. Also tested for an archived study, and no biospecimens were displayed
2.4.7 | A user with access to a substudy can identify the collections and biospecimens for a patient for only that substudy in context when viewing the Subject > Subject Biospecimen tab from the context of the substudy. | 1. Log in as a user with access to WARTN and all of its substudies. 2. Under Study > Study Details, enter the context of the WARTN substudy. 3. Under Subject > Demographic Data, enter the context of a patient with biospecimens associated to multiple active substudies, and an archived substudy. 4. In the Subject > Biospecimen tab, identify the collections associated with active substudies, and the collections assosciated with archived substudies. | 1. The user is able to view the Subject > Subject Biospecimen tab from the context of the child study. 2. The user is able to see all collections, biospecimens, and transactions assigned to the substudy. 3. The user is unable to identify collections, biospecimens, or transactions assigned to archived substudies. | 1. The user is unable to view the Subject > Subject Biospecimen tab from the context of the sub study. 2. The user is unable to see all collections, biospecimens, and transactions assigned to active substudies. 3. The user is able to identify collections, biospecimens, or transactions assigned to archived substudies. | Lisa | 2013-08-07 | 1 | Lisa; “ I am happy to accept that you can see a list of substudies the patient has consented to when in the Subject page of the parent study but you have to be in the context of the substudy to see the collections and biospecimens for that substudy. The vast majority of our patients are only in one study and we have no patients in more than two so its not a big deal practically. Happy to sign off.”
2.4.8 | A user with access to a substudy can identify the collections and biospecimens for a patient for the substudies when viewing the Subject > Biospecimen tab from the context of the substudy. | 1. Log in as a user with access to WARTN and all of its substudies. 2. Under Study > Study Details, enter the context of the WARTN substudy. 3. Under Subject > Demographic Data, enter the context of a patient with biospecimens associated to multiple active substudies, and an archived substudy. 4. In the Subject > Biospecimen tab, identify the biospecimens associated with active substudies, and thebiospecimens assosciated with archived substudies. | 1. The user is able to view the Subject > Biospecimen tab from the context of the parent study. 2. The user is able to see all collections, biospecimens, and transactions assigned to active substudies. 3. The user is unable to identify collections, biospecimens, or transactions assigned to archived substudies. | 1. The user is unable to view the Subject > Biospecimen tab from the context of the parent study. 2. The user is unable to see all collections, biospecimens, and transactions assigned to active substudies. 3. The user is able to identify collections, biospecimens, or transactions assigned to archived substudies. | Lisa | 8/7/2013 12.05 | 1 | Lisa; “ I am happy to accept that you can see a list of substudies the patient has consented to when in the Subject page of the parent study but you have to be in the context of the substudy to see the collections and biospecimens for that substudy. The vast majority of our patients are only in one study and we have no patients in more than two so its not a big deal practically. Happy to sign off.” | to be disussed
2.4.10 | A user with access to a study and all of its substudies cannot enter the Subject > Demographic Data page for a subject in the context of an archived substudy. | 1. Log in as a user with access to WARTN and all of its substudies. 2. Under Study > Study Details, enter the context of the WARTN study. 3. Under Subject > Demographic Data, enter the context of a patient known to have biospecimens associated to an active substudy, and an archived substudy. 3. In the Subject > Demographic Data page for a subject, find and click the name of an archived substudy in the "Link to Child Study Subject" list. 4. Click the Subject > Demographic Data tab. 5. Identify the same patient and enter the Subject > Demographic Data page. | 1. The user is unable to view the Subject > Demographic Data page for a subject from the context of an archived study. 2. The user is unable to identify if a patient is associated with an archived study from the Subject > Demographic Data page. 3. The user is able to identify which active studies a patient is associated with from the Subject > Demographic Data page. | 1. The user is able to view the Subject > Demographic Data page for a subject from the context of an archived study. 2. The user is able to identify if a patient is associated with an archived study from the Subject > Demographic Data page. 3. The user is unable to identify which active studies a patient is associated with from the Subject > Demographic Data page. | Lisa | 2013-08-07 | 1 | user is unable to enter the context of an archived study in the subject demographic data tab.
2.4.11 | A user with access to a study and all of its substudies cannot identify Archived substudies in the "Study" value list in the Subject > Biospecimen tab. | 1. Log in as a user with access to WARTN and all of its substudies. 2. Under Study > Study Details, enter the context of the WARTN study. 3. Under Subject > Demographic Data, enter the context of a patient known to have biospecimens associated to an active substudy, and an archived substudy. 3. In the Subject > Biospecimen tab, find the name of an archived substudy in the "Study" value list. | 1. The user is able to view the Subject > Biospecimen tab from the context of a patient in multiple substudies. 2. The user is unable to identify archived studies in the Subject > Biospecimen "Study" value list. 3. The user is able to identify all active substudies in the Subject > Biospecimen "Study" value list. | 1. The user is unable to view the Subject > Biospecimen tab from the context of a patient in multiple substudies. 2. The user is able to identify archived studies in the Subject > Biospecimen "Study" value list. 3. The user is unable to identify all active substudies in the Subject > Biospecimen "Study" value list. | Lisa | 2013-08-07 | 1
2.4.12 | A user with access to a study and all of its substudies cannot identify the patients, transactions, or biospecimens associated with archived substudies from within the Subject > Biospecimen tab. | 1. Log in as a user with access to WARTN and all of its substudies. 2. Under Study > Study Details, enter the context of the WARTN study. 3. Under Subject > Demographic Data, enter the context of a patient known to have biospecimens associated to an active substudy, and an archived substudy. 4. In the Subject > Biospecimen tab, find a patient with a known association to an active substudy and an archived substudy. 5. Attempt to identify which substudies the patient is associated with. | 1. The user is able to view the Subject > Biospecimen tab from the context of a patient in multiple substudies. 2. The user is unable to identify patients assigned to arhived studies. 3. The user is able to identify all patients, transactions, or biospecimens assigned to all active studies. | 1. The user is unable to view the Subject > Biospecimen tab from the context of a patient in multiple substudies. 2. The user is able to identify patients, transactions, or biospecimens assigned to archived studies. 3. The user is unable to identify all patients, transactions, and biospecimens assigned to all active studies. | Lisa | 406735.0208 | 1 | user is unable to enter the context of an archived study in the subject biospecimen tab and view archived collections, biospecimens, and transactions
2.4.13 | A user with access to a study and all of its substudies cannot identify Archived substudies in the "Study" value list in the LIMS > Subject Detail tab. | 1. Log in as a user with access to WARTN and all of its substudies. 2. Under Study > Study Details, enter the context of the WARTN study. 3. In the LIMS > Subject Detail tab, find the name of an archived substudy in the "Study" value list. | 1. The user is able to view the LIMS > Subject Detail tab from the context of the WARTN study. 2. The user is unable to identify archived studies in the LIMS > Subject Detail "Study" value list. 3. The user is able to identify all active substudies in the LIMS > Subject Detail "Study" value list. | 1. The user is unable to view the LIMS > Subject Detail tab from the context of the WARTN study. 2. The user is able to identify archived studies in the LIMS > Subject Detail "Study" value list. 3. The user is unable to identify all active substudies in the LIMS > Subject Detail "Study" value list. | LISA | 2013-08-07 00:33 | 1
2.4.14 | A user with access to a study and all of its substudies cannot identify the patients, transactions, or biospecimens associated with archived substudies from within the LIMS > Subject Detail tab. | 1. Log in as a user with access to WARTN and all of its substudies. 2. Under Study > Study Details, enter the context of the WARTN study. 3. In the LIMS > Subject Detail tab, find a patient with a known association to an active substudy and an archived substudy. 4. Attempt to identify which substudies the patient is associated with. | 1. The user is able to view the LIMS > Subject Detail tab from the context of the WARTN study. 2. The user is unable to identify patients assigned to archived studies. 3. The user is able to identify all patients assigned to all active studies. | 1. The user is unable to view the LIMS > Subject Detail tab from the context of the WARTN study. 2. The user is able to identify patients assigned to an archives study. 3. The user is unable to identify all patients assigned to all active studies. | Lisaq | 2013-08-07 00:35 | 1 | user is unable to enter the context of an archived study in the LIMS subject detail tab.
2.4.15 | A user with access to a study and all of its substudies cannot identify Archived substudies in the "Study" value list in the LIMS > Biospecimen tab. | 1. Log in as a user with access to WARTN and all of its substudies. 2. Under Study > Study Details, enter the context of the WARTN study. 3. Under LIMS > Subject Detail, enter the context of a patient known to have biospecimens associated to an active substudy, and an archived substudy. 3. In the LIMS > Biospecimen tab, find the name of an archived substudy in the "Study" value list. | 1. The user is able to view the LIMS > Biospecimen tab from the context of a patient in multiple substudies. 2. The user is unable to identify the archived study in the LIMS > Biospecimen "Study" value list. 3. The user is able to identify all active substudies in the LIMS > Biospecimen "Study" value list. | 1. The user is unable to view the LIMS > Biospecimen tab from the context of a patient in multiple substudies. 2. The user is able to identify the archived study in the LIMS > Biospecimen "Study" value list. 3. The user is unable to identify all active substudies in the LIMS > Biospecimen "Study" value list. | Lisa | 2013-08-07 00:37 | 1
2.4.16 | A user with access to a study and all of its substudies cannot identify the patients, transactions, or biospecimens associated with archived substudies from within the LIMS > Biospecimen tab. | 1. Log in as a user with access to WARTN and all of its substudies. 2. Under Study > Study Details, enter the context of the WARTN study. 3. Under LIMS > Subject Detail, enter the context of a patient known to have biospecimens associated to an active substudy, and an archived substudy. 4. In the LIMS > Biospecimen tab, find a patient with a known association to an active substudy and an archived substudy. 5. Attempt to identify which substudies the patient is associated with. | 1. The user is able to view the LIMS > Biospecimen tab from the context of a patient in multiple substudies. 2. The user is unable to identify patients, transactions, or biospecimens assigned to the archived study. 3. The user is able to identify all patients, transactions, and biospecimens assigned to all active studies. | 1. The user is unable to view the LIMS > Biospecimen tab from the context of a patient in multiple substudies. 2. The user is able to identify patients, transactions, or biospecimens assigned to the archived study. 3. The user is unable to identify all patients, transactions, and biospecimens assigned to all active studies. | Lisa | 2013-08-07 00:38 | 1 | user is unable to enter the context of an archived study in the Subject → Biospecimen Search tab and the biospecimen details pages
2.4.17 | A user with access to a study and all of its substudies cannot identify Archived substudies in the "Study" value list in the LIMS > Subject Detail tab. | 1. Log in as a user with access to WARTN and all of its substudies. 2. Find a previously archived study in the Study > Study Details tab. 3. In the LIMS > Subject Detail tab, find the name of an archived substudy in the "Study" value list. | 1. The user is unable to identify the archived study in the Subject > Demographic Data "Study" value list. 2. The user is unable to identify patients assigned to the archived study. | 1. The user is able to identify the archived study in the Subject > Demographic Data "Study" value list. 2. The user is able to identify patients assigned to the archived study. | Lisa | 2013-08-07 12:39 | 1
2.5 | Fields
2.5.1 | The "Study > Study Details" page for a specific study or substudy contains an appropriate field for entry of the "study name" | 1. Log in as a user with "Study Administrator" access to a study and all of its substudies. 2. Click the first study in the list of studies under the Study > Study Details tab. 3. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-08-07 12:39 | 1
2.5.2 | The "Study > Study Details" page for a specific study or substudy contains an appropriate field for entry of the study "primary investigator" | 1. Log in as a user with "Study Administrator" access to a study and all of its substudies. 2. Click the first study in the list of studies under the Study > Study Details tab. 3. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-08-07 12:39 | 1
2.5.4 | The "Study > Study Details" page for a specific study or substudy contains an appropriate field for entry of the study "contact person" | 1. Log in as a user with "Study Administrator" access to a study and all of its substudies. 2. Click the first study in the list of studies under the Study > Study Details tab. 3. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-08-07 12:39 | 1
2.5.5 | The "Study > Study Details" page for a specific study or substudy contains an appropriate field for entry of the study "contact phone" | 1. Log in as a user with "Study Administrator" access to a study and all of its substudies. 2. Click the first study in the list of studies under the Study > Study Details tab. 3. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-08-07 12:39 | 1
2.5.9 | The "Study > Study Details" page for a specific study or substudy contains an appropriate field for entry of the study "description" | 1. Log in as a user with "Study Administrator" access to a study and all of its substudies. 2. Click the first study in the list of studies under the Study > Study Details tab. 3. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-08-07 12:39 | 1
2.5.10 | The "Study > Study Details" page for a specific study or substudy contains an appropriate field for entry of the study "start date". | 1. Log in as a user with "Study Administrator" access to a study and all of its substudies. 2. Click the first study in the list of studies under the Study > Study Details tab. 3. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-08-07 12:39 | 1 | can use “Date of Application”
2.5.12 | The "Study > Study Details" page for a specific study or substudy contains an appropriate field for entry of the "parent study" | 1. Log in as a user with "Study Administrator" access to a study and all of its substudies. 2. Click the first study in the list of studies under the Study > Study Details tab. 3. Identify that an appropriate field exists. | 1. The field exists 2. The field location and format are suitable to meet the user's requirements. 3. Data entry to the field is possible in a context appropriate to its use. 4. The test user considers all value lists and check box options associated with the field to be appropriate. | 1. The field does not exists 2. The field location and format do not meet the user's requirements. 3. Data entry to the field is not possible in the context appropriate to its use. 4. The test user does not consider all value lists and check box options associated with the field to be appropriate. | Lisa | 2013-08-07 12:39 | 1
CONSENT
| A user with "Subject Data Manager" or higher access for a study and its substudies can create consents for substudies which are independent to those of the parent study | 1. Log in as a user with "Subject Data Manager" access to WARTN and all substudies. 2. In Study > Study Details, enter the context of the WARTN study. 3. In Subject > Demographic Data, find a subject with the surname "Beilin". 4. Remove consent for the WARTN study. 5. Under Study > Study Details, enter the context of the Colorectal Cancer Collection study. 6. In LIMS > Subject Data, find the same patient. 7. Identify if removal from WARTN affected consent to substudies. |  |  | Lisa | 2013-08-07 12:40 | 1
| A user with "Subject Data Manager" or higher access for a study and its substudies can allocate a consent to select list of studies or substudies | 1. Log in as a user with "Subject Data Manager" access to WARTN and all substudies. 2. For allsub -studies that will be auto-consented, select Auto-consent” and click “Save”. 3. In Study > Study Details, enter the context of the WARTN study. 4. In Subject > Demographic Data, find a subject with the surname "Beilin". 4. Select all sub-studies the subject is participating in. 5. Click “Save”. | 1. The subject is consented to all specified sub-studies. | 1. The subject is consented to all specified sub-studies. | Lisa | 2013-08-07 12:50 | 1
| A user with "Subject Read-Only" or higher access for a study and its substudies can search for a patient's consent status for a study or substudy | 1. Log in as a user with "Subject Read-Only" access to WARTN and its substudies 2. ..see if the CRC substudy and WARTN study consent status for an individual patient can be searched under the "Subject > Demographic Data" tab. | 1. The user is able to search for a consent status for the study. 2. The user is able to search for a consent status for the substudy. 3. The user can see a history of the consent status for the study. |  | Lisa | 2013-08-07 12:52 | 1 | Can run a report to determine all patients/subjects for a particular consent status and a particular subject.
| USER EXPERIENCE: There should be no confusion as to whether a consent is at the study or substudy level | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | Lisa | 2013-08-07 12:54 | 1
SUBJECTS
Numbering
| The database allows for sequential patient numbering across all studies and substudies (P01234). | The database allows for sequential patient numbering across all studies and substudies (P01234). |  |  | Lisa | 2013-08-07 12:45 | 1 | subject identification can be set to requested format
COLLECTIONS
New Collections
| A user with "LIMS Data Manager" access to a study can define new collections. | 1. Log in as a user with "Subject Read-Only" access to WARTN. 2. Click on the WARTN study in the Study Details tab. 3. Search for a subject, or click any of the subject links available. 4. Select a linke d sub-study to bring into context. 5. Click the “Subject Biospecimen” tab. 6. Click “New” button under the collections list. 7. Enter details as required. 8. Click “Save” | 1. The user is able to create a new collection for a subject. | 1. The user is able to create a new collection for a subject. | Lisa | 2013-08-07 13:00 | 1 | new collection created successfully
| A user with "LIMS Read-Only" access to a study cannot define new collections. | 1. Log in as a user with "Subject Read-Only" access to WARTN. 2. Click on the WARTN study in the Study Details tab. 3. Search for a subject, or click any of the subject links available. 4. Select a linke d sub-study to bring into context. 5. Click the “Subject Biospecimen” tab. 6. Click “New” button under the collections list. 7. Enter details as required. 8. Click “Save” | 1. The user is unable to create a new subject. | 1. The user is unable to create a new subject. | Lisa | 2013-08-07 13:05 | 1 | unable to create new collections
Numbering
| sequential collection numbering across all studies and substudies (C-01234) | 1. Log in as a user with "Study Administrator" access to WARTN and all its substudies. 2. Click WARTN in the list of studies under the Study > Study Details tab. 3. Click the first subject in the list of subjects under the Subject > Demographic Data tab. 4. Click “Study-specific Demographic Data” tab 5. Add/Edit data against he custom fields accordingly |  |  | Lisa | 2013-08-07 11:46 | 1
| A user with sufficient access can maintain study-specific and substudy specific custom fields for collections, on a per-study or per-substudy basis. | A user with sufficient access can maintain study-specific and substudy specific custom fields for collections, on a per-study or per-substudy basis. |  |  | Lisa | 2013-08-07 11:46 | 1
| USER EXPERIENCE: When a collection is in context, a list of associated biospecimens should be accessible on every page. | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | Lisa | 2013-08-07 11:47 | 1 | use tree to the left
| USER EXPERIENCE: When a collection is in context, the study or substudy that the collection is associated with should be readily visible. | The user will review user experience items during normal testing and pass or fail this item after completion. | 1. The location and format of the data is suitable to meet the user's requirements. | 1. The location and format of the data is not suitable to meet the user's requirements. | Lisa | 2013-08-07 11:47 | 1
SECURITY & BACKUP
| Users of all access levels should only be able to see the studies and substudies they have access to. Note that a parent study permission is passed down to substudies |  |  |  | Lisa | in discussion